## Sheet1
Phase 1: Move the other account SQS to new AWS account
Sno | Risk | Probability | Impact | Explanation
| Service Disruption during SQS Migration | 4 | 4 | There is a high probability of service disruption while migrating the SQS to a new AWS account, potentially affecting message processing.
| Security Vulnerabilities during Migration | 2 | 4 | While the probability of security vulnerabilities is low, their impact can be significant, leading to potential data breaches or unauthorized access.
| Cost Overruns during Migration | 3 | 3 | There is a moderate probability of cost overruns due to complexities and unanticipated expenses during the migration process.
Dependencies:
| Dependency | Probability | Impact | Explanation
| Dependency on AWS Services | 3 | 3 | There is a moderate probability of dependency on AWS services, which could impact the migration.
Phase 2: Move DB from on-premises to AWS first and make Kubernetes (REST API services) to call DB from AWS
| Risk | Probability | Impact | Explanation
| Data Loss during DB Migration | 3 | 4 | There is a moderate probability of data loss during the migration of the database from on-premises to AWS.
| Compatibility Issues between Kubernetes and AWS ECS | 2 | 4 | There is a low probability of compatibility issues between Kubernetes-based REST API services and AWS ECS, but it could impact functionality.
| Performance Impact during Kubernetes to AWS ECS Migration | 3 | 3 | There is a moderate probability of performance impact during the migration from Kubernetes to AWS ECS due to differences in underlying systems.
| Security Vulnerabilities during Migration | 2 | 4 | While the probability of security vulnerabilities is low, their impact can be significant, leading to potential data breaches or unauthorized access.
| Cost Overruns during Migration | 3 | 3 | There is a moderate probability of cost overruns due to complexities and unanticipated expenses during the migration process.
Dependencies:
| Dependency | Probability | Impact | Explanation
| Dependency on AWS Services | 3 | 3 | There is a moderate probability of dependency on AWS services, which could impact the migration.
Phase 3: Move the REST API Services Kubernetes to ECS and Move the UI Kubernetes to ECS
| Risk | Probability | Impact | Explanation
| Compatibility Issues between Kubernetes and AWS ECS | 2 | 4 | There is a low probability of compatibility issues between Kubernetes-based REST API services and AWS ECS, but it could impact functionality.
| Performance Impact during Kubernetes to AWS ECS Migration | 3 | 3 | There is a moderate probability of performance impact during the migration from Kubernetes to AWS ECS due to differences in underlying systems.
| Cost Overruns during Migration | 3 | 3 | There is a moderate probability of cost overruns due to complexities and unanticipated expenses during the migration process.
Dependencies:
| Dependency | Probability | Impact | Explanation
| Dependency on AWS Services | 3 | 3 | There is a moderate probability of dependency on AWS services, which could impact the migration.
Phase 4: Setup the backup and recovery in another region
| Risk | Probability | Impact | Explanation
| Backup and Recovery Setup in Another Region | 3 | 3 | There is a moderate probability of challenges during the setup of backup and recovery in another region, affecting Disaster Recovery capabilities.
Dependencies:
| Dependency | Probability | Impact | Explanation
| Dependency on AWS Services | 3 | 3 | There is a moderate probability of dependency on AWS services, which could impact the migration.

## Sheet2
Phase 1: Move the other account SQS to new AWS account
Risk | Probability | Impact | Explanation | Mitigation Plan
Service Disruption during SQS Migration | 4 | 4 | There is a high probability of service disruption while migrating the SQS to a new AWS account, potentially affecting message processing. | - Schedule the migration during off-peak hours to minimize the impact on users. - Implement gradual migration with a fallback plan in case of issues. - Conduct thorough testing and validation of the SQS migration before cutover. - Have clear communication with stakeholders about the planned migration and expected downtime.
Security Vulnerabilities during Migration | 2 | 4 | While the probability of security vulnerabilities is low, their impact can be significant, leading to potential data breaches or unauthorized access. | - Follow AWS security best practices and apply appropriate security measures during the migration. - Conduct security assessments before and after migration to identify and address potential vulnerabilities. - Monitor the AWS account closely for any suspicious activities during and after migration. - Educate the team about security best practices and promote a security-first mindset.
Cost Overruns during Migration | 3 | 3 | There is a moderate probability of cost overruns due to complexities and unanticipated expenses during the migration process. | - Plan the migration carefully with a clear understanding of costs and budget. - Monitor AWS resource usage and expenses during the migration. - Utilize AWS cost management tools and services to set cost controls and alarms. - Regularly review and optimize AWS resources to avoid unnecessary costs. - Involve finance and budget stakeholders in the migration planning to ensure cost transparency and control.
Phase 2: Move DB from on-premises to AWS first and make Kubernetes (REST API services) to call DB from AWS
Risk | Probability | Impact | Explanation | Mitigation Plan
Data Loss during DB Migration | 3 | 4 | There is a moderate probability of data loss during the migration of the database from on-premises to AWS. | - Perform thorough backups of the on-premises database before initiating the migration. - Conduct a test migration with a copy of the production data to validate the process and identify potential issues. - Implement data validation checks during and after migration to ensure data integrity. - Have a rollback plan in case of data loss or critical issues during migration.
Compatibility Issues between Kubernetes and AWS ECS | 2 | 4 | There is a low probability of compatibility issues between Kubernetes-based REST API services and AWS ECS, but it could impact functionality. | - Conduct a detailed assessment of application dependencies and requirements before migration. - Use container registries and CI/CD pipelines to ensure consistent deployments in Kubernetes and AWS ECS. - Perform thorough testing in the AWS ECS environment to validate compatibility. - Consider using tools like AWS App Runner or AWS EKS if Kubernetes compatibility is critical to the application.
Performance Impact during Kubernetes to AWS ECS Migration | 3 | 3 | There is a moderate probability of performance impact during the migration from Kubernetes to AWS ECS due to differences in underlying systems. | - Monitor application performance and resource utilization during and after migration. - Optimize AWS ECS configurations and scaling settings to match Kubernetes performance levels. - Fine-tune the ECS environment based on performance testing results. - Implement performance testing and load testing before migration to identify and address performance bottlenecks.
Security Vulnerabilities during Migration | 2 | 4 | While the probability of security vulnerabilities is low, their impact can be significant, leading to potential data breaches or unauthorized access. | - Follow AWS security best practices and apply appropriate security measures during the migration. - Conduct security assessments before and after migration to identify and address potential vulnerabilities. - Monitor the AWS ECS environment closely for any suspicious activities during and after migration. - Educate the team about security best practices and promote a security-first mindset.
Cost Overruns during Migration | 3 | 3 | There is a moderate probability of cost overruns due to complexities and unanticipated expenses during the migration process. | - Plan the migration carefully with a clear understanding of costs and budget. - Monitor AWS resource usage and expenses during the migration. - Utilize AWS cost management tools and services to set cost controls and alarms. - Regularly review and optimize AWS resources to avoid unnecessary costs. - Involve finance and budget stakeholders in the migration planning to ensure cost transparency and control.
Phase 3: Move the REST API Services Kubernetes to ECS and Move the UI Kubernetes to ECS
Risk | Probability | Impact | Explanation | Mitigation Plan
Compatibility Issues between Kubernetes and AWS ECS | 2 | 4 | There is a low probability of compatibility issues between Kubernetes-based REST API services and AWS ECS, but it could impact functionality. | - Conduct a detailed assessment of application dependencies and requirements before migration. - Use container registries and CI/CD pipelines to ensure consistent deployments in Kubernetes and AWS ECS. - Perform thorough testing in the AWS ECS environment to validate compatibility. - Consider using tools like AWS App Runner or AWS EKS if Kubernetes compatibility is critical to the application.
Performance Impact during Kubernetes to AWS ECS Migration | 3 | 3 | There is a moderate probability of performance impact during the migration from Kubernetes to AWS ECS due to differences in underlying systems. | - Monitor application performance and resource utilization during and after migration. - Optimize AWS ECS configurations and scaling settings to match Kubernetes performance levels. - Fine-tune the ECS environment based on performance testing results. - Implement performance testing and load testing before migration to identify and address performance bottlenecks.
Cost Overruns during Migration | 3 | 3 | There is a moderate probability of cost overruns due to complexities and unanticipated expenses during the migration process. | - Plan the migration carefully with a clear understanding of costs and budget. - Monitor AWS resource usage and expenses during the migration. - Utilize AWS cost management tools and services to set cost controls and alarms. - Regularly review and optimize AWS resources to avoid unnecessary costs. - Involve finance and budget stakeholders in the migration planning to ensure cost transparency and control.
Phase 4: Setup the backup and recovery in another region
Risk | Probability | Impact | Explanation | Mitigation Plan
Backup and Recovery Setup in Another Region | 3 | 3 | There is a moderate probability of challenges during the setup of backup and recovery in another region, affecting Disaster Recovery capabilities. | - Plan the backup and recovery setup carefully, considering the region's geographical distance and network connectivity. - Test the backup and recovery procedures in the target region to ensure they work as expected. - Implement monitoring and alerting for backup status and recovery readiness. - Have a clear communication plan for stakeholders about the backup and recovery process.