## Sheet2
Sno | Team Name | Problem Summary | Problem Details | Priority | Proposed Solution | Timeline | Assigned To | Status | Resolution Notes | Follow-up
1 |  | Data ingestion process failing for new data sources | The automated data ingestion process is encountering errors when attempting to ingest data from newly added data sources. This is causing delays in making the data available for analysis. | High | Investigate and fix the root cause of the data ingestion failures. Implement improvements to handle new data sources seamlessly in the future. | Within 1 week |  | In Progress | Investigated logs and identified an issue with data source validation. Implemented a fix and reprocessed the failed data. Monitoring the process for further validation. | Schedule a meeting with Data Governance Team to discuss adding new data sources to the data ingestion process.
2 |  | Slow data loading into the Data Warehouse | The data loading process into the Data Warehouse is taking longer than expected, leading to delays in data availability for reporting and analysis. | Medium | Optimize the data loading pipeline, improve data extraction and transformation efficiency, and consider partitioning or parallel processing. | Within 2 weeks | John Doe (Data Engineer) | In Progress | Identified data processing bottlenecks and made optimizations. Monitoring the loading times for improvement validation. | Coordinate with the Data Quality Team to validate data integrity after the optimizations.
3 |  | Data discrepancies in reports | There are discrepancies in the data presented in various reports generated from the Data Warehouse, causing confusion among stakeholders. | High | Conduct a data quality assessment, identify data anomalies, and address data integration and transformation issues. | Within 1 week | Jane Smith (Business Intelligence Analyst) | In Progress | Identified data integration errors and corrected data mappings. Rerun reports to validate accuracy. | Schedule a meeting with stakeholders to communicate the issue resolution and discuss improved data validation processes.
4 |  | Data access permission discrepancies | Users are experiencing inconsistencies in data access permissions within the Data Warehouse, leading to unauthorized data access. | High | Conduct an access control review, audit user permissions, and rectify discrepancies in data access settings. | Within 48 hours | Michael Brown (Data Governance Analyst) | Pending | Investigation ongoing to identify the root cause of permission discrepancies and devise a comprehensive solution. | Implement a data access review process to ensure timely review and updates of user permissions.